## SINF Gantt chart
Task Name | Start Date | Day of Project | End Date | Workload (in days) | Workload complete | Workload remaining | Completion Rate (%) | Weeks | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9
2020-10-15 | Phase 1
Project Goals Assessment | 2020-10-16 | 1 | 2020-10-18 | 2 | 2 | 0 | 100%
Project Planning | 2020-10-17 | 2 | 2020-10-20 | 3 | 3 | 0 | 100%
Web Mockups | 2020-10-19 | 4 | 2020-10-24 | 5 | 5 | 0 | 100%
Information Architecture | 2020-10-20 | 5 | 2020-10-28 | 8 | 8 | 0 | 100%
Specification Report | 2020-10-26 | 11 | 2020-11-07 | 12 | 12 | 0 | 100%
Phase 2
Dev Environment Setup | 2020-11-04 | 20 | 2020-11-08 | 4 | 4 | 0 | 100%
Specification and Dev of Web Routes | 2020-11-06 | 22 | 2020-11-12 | 6 | 6 | 0 | 100%
Overview Dashboard Dev | 2020-11-09 | 25 | 2020-11-16 | 7 | 7 | 0 | 100%
Dashboards Boilerplate Dev + Initial connection | 2020-11-14 | 30 | 2020-11-16 | 2 | 2 | 0 | 100%
Phase 3
Financial Dashboard Dev | 2020-11-16 | 32 | 2020-11-24 | 8 | 8 | 0 | 100%
Financial Jasmin Conection | 2020-11-17 | 33 | 2020-11-20 | 3 | 3 | 0 | 100%
Sales Dashboard Dev | 2020-11-18 | 34 | 2020-11-26 | 8 | 8 | 0 | 100%
Sales Jasmin Conection | 2020-11-20 | 36 | 2020-11-23 | 3 | 3 | 0 | 100%
Procurement Dashboard Dev | 2020-11-22 | 38 | 2020-11-30 | 8 | 8 | 0 | 100%
Inventory Dashboard Dev | 2020-11-24 | 40 | 2020-12-02 | 8 | 7.2 | 0.8 | 90%
Procurement Jasmin Connection | 2020-11-25 | 41 | 2020-11-28 | 3 | 3 | 0 | 100%
Inventory Jasmin Conection | 2020-11-25 | 41 | 2020-12-01 | 6 | 4.2 | 1.8 | 70%
Frontend tasks | 2020-11-20 | 36 | 2020-12-01 | 11 | 11 | 0 | 100%
Backend tasks | 2020-11-25 | 41 | 2020-12-14 | 19 | 19 | 0 | 100%
Product-Specific Dashboard Dev | 2020-11-26 | 42 | 2020-12-04 | 8 | 8 | 0 | 100%
Product-Specific Jasmin Conection | 2020-11-27 | 43 | 2020-12-03 | 6 | 6 | 0 | 100%
Overview Dashboard Dev | 2020-11-29 | 45 | 2020-12-07 | 8 | 8 | 0 | 100%
Overview Connection | 2020-12-03 | 49 | 2020-12-06 | 3 | 3 | 0 | 100%
Final Report | 2020-12-16 | 62 | 2020-12-19 | 3 | 3 | 0 | 100%

## Basic Gantt Chart Template (hidden)
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 3 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 3 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 5 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 5 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 6 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 3 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 7 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 2 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 4 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 4 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 1 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 4 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 3 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 3 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 9 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 5 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 6 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 1 | Rachel | 0%

## Manual Gantt Chart Template (hidden)
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 3 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 5 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 4 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 3 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 3 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 5 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 9 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 3 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 5 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 5 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 4 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 5 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 3 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 5 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 4 | Rachel | 40%